## Jira_Backlog
Issue ID | Issue Type | Title | Description | Story Points | Priority | Assigned To | Sprint | Branch Name | Status
LT-0 | Task | Create Documentation | Create SRS. Jira Task Sheet, Presentation, Final Report | 4 | High | Pawan Sharma | Sprint 0 | document-setup | To Do
LT-1 | Task | Project Setup & Architecture | Setup Flask project, folder structure, and architecture design. | 8 | High | Pawan Sharma | Sprint 1 | feature/project-setup | To Do
LT-2 | Task | Frontend UI Design | Create responsive UI with text input and translate button. | 5 | High | Rahul Verma | Sprint 1 | feature/frontend-ui | To Do
LT-3 | Task | Model Integration | Integrate Helsinki-NLP/opus-mt-en-hi model with Flask backend. | 13 | High | Anjali Singh | Sprint 1 | feature/model-integration | To Do
LT-4 | Task | Tokenizer Implementation | Implement MarianTokenizer for text preprocessing. | 5 | Medium | Rahul Verma | Sprint 1 | feature/tokenizer | To Do
LT-5 | Task | Translation API Route | Create /translate API endpoint in Flask. | 8 | High | Pawan Sharma | Sprint 2 | feature/api-translate | To Do
LT-6 | Task | Error Handling | Handle empty input and server errors. | 3 | Medium | Anjali Singh | Sprint 2 | feature/error-handling | To Do
LT-7 | Task | Deployment on Render | Deploy Flask app using Gunicorn on Render. | 8 | High | Pawan Sharma | Sprint 2 | feature/render-deployment | To Do
LT-8 | Task | Create requirements.txt & Procfile | Add required dependencies and Procfile for deployment. | 3 | Medium | Rahul Verma | Sprint 2 | chore/deployment-config | To Do
LT-9 | Task | Performance Optimization | Optimize model loading and response time. | 5 | Medium | Anjali Singh | Sprint 3 | feature/performance-optimization | To Do
LT-10 | Task | UI Enhancements | Improve UI styling and responsiveness. | 5 | Low | Rahul Verma | Sprint 3 | feature/ui-enhancement | To Do
LT-11 | Task | Testing & Bug Fixing | Perform unit testing and fix identified bugs. | 8 | High | Pawan Sharma | Sprint 3 | feature/testing | To Do
LT-12 | Task | Documentation & README | Prepare project documentation and deployment guide. | 3 | Medium | Anjali Singh | Sprint 3 | docs/project-documentation | To Do